## Edit Schedule
Week | Phase | Editor | Start Date | End Date | Scenes | Hours Budgeted | Hours Used | Status
W1 | Assembly Cut | Ahmed Al Blooshi | 2026-10-26 | 2026-10-30 | 1-4 | 40 | 0 | Not Started
W2 | Assembly Cut | Ahmed Al Blooshi | 2026-11-02 | 2026-11-06 | 5-9 | 40 | 0 | Not Started
W3 | Assembly Cut | Ahmed Al Blooshi | 2026-11-09 | 2026-11-13 | 10-14 | 40 | 0 | Not Started
W4 | Rough Cut | Ahmed Al Blooshi | 2026-11-16 | 2026-11-20 | All | 40 | 0 | Not Started
W5 | Director Review | Yousef Al Saedi | 2026-11-23 | 2026-11-27 | All | 32 | 0 | Not Started
W6 | Fine Cut v1 | Ahmed Al Blooshi | 2026-11-30 | 2026-12-04 | All | 40 | 0 | Not Started
W7 | Producer Review | Sara Al Kindy | 2026-12-07 | 2026-12-11 | All | 32 | 0 | Not Started
W8 | Picture Lock Prep | Ahmed Al Blooshi | 2026-12-14 | 2026-12-18 | All | 40 | 0 | Not Started
W9 | Picture Lock | All stakeholders | 2026-12-21 | 2026-12-23 | All | 24 | 0 | Not Started
W10-11 | Color Grading | Reem Al Falasi | 2027-01-04 | 2027-01-15 | All | 80 | 0 | Not Started
W12 | Sound Design | Salem Al Zaabi | 2027-01-18 | 2027-01-22 | All | 40 | 0 | Not Started
W13 | Music Score | Composer (TBC) | 2027-01-25 | 2027-01-29 | All | 40 | 0 | Not Started
W14 | Final Mix | Salem Al Zaabi | 2027-02-01 | 2027-02-05 | All | 40 | 0 | Not Started
W15 | VFX Integration | Khalid Al Mazrouei | 2027-02-08 | 2027-02-12 | 12 + 14 augmentation | 40 | 0 | Not Started
W16 | Mastering & Delivery | Reem Al Falasi | 2027-02-15 | 2027-02-19 | All | 40 | 0 | Not Started